## Start Here
🔎 mysleepytale — 15-Day Google Indexing Sprint
Goal: get all 50 'discovered but not indexed' pages into Google within 15 days.
The gap (where we are vs where we need to be)
Now | Google has crawled/discovered 50 URLs but hasn't indexed them. They won't show in search until indexed.
Likely causes | New-ish domain & low authority, thin/duplicate signals, few internal links, almost no backlinks, and 3 SPA routes that are JavaScript-only (Google struggles to render them).
Target | 50/50 indexed (or a clear fix-list for any stragglers) in 15 days.
The plan = 2 tracks (run both at once)
TRACK A — Technical (does 80% of the work) | Search Console sitemap + 'Request Indexing', internal links, a few real backlinks, fix the SPA pages, IndexNow. → See 'Indexing Checklist' tab. Owner-led.
TRACK B — Social distribution (you + 4 friends) | Each person shares their assigned links on FB / X / LinkedIn / IG / WhatsApp groups. Drives discovery + traffic, which nudges Google to crawl. → See 'Link Distribution' tab.
How the team uses this file
1. Each person opens 'Link Distribution', filters Owner = their name → that's their 10 links + ready-made example posts.
2. Share ~1 link/day on the suggested platform. Copy the example post, paste, add the link. Mark Status = Shared.
3. The owner works the 'Indexing Checklist' + 'Daily Schedule (15 Days)' in parallel.
4. Check progress on 'Team Summary'. Re-share stragglers on a 2nd platform in week 2.
▸ Honest expectation: Google decides final timing — we can't force it. But sitemap + Request Indexing + internal links + fixing the SPA pages is what actually moves the needle. Social shares help discovery; they are not a guaranteed index button. Doing all of it together is how we hit 15 days.

## Gap & Action Plan
# | Action (what to do) | Why it matters for indexing | Track | Owner | By day
1 | Verify Google Search Console + submit/re-submit sitemap.xml | Google needs an up-to-date sitemap to know all 50 URLs exist and re-crawl them. | Technical | Owner | Day 1
2 | URL Inspection → 'Request Indexing' for Priority 1 URLs | The single most direct way to ask Google to index a specific page (quota ~10–15/day). | Technical | Owner | Day 2
3 | Add internal links: homepage + already-indexed pages → these 50 URLs | Internal links pass crawl signals; orphan pages rarely get indexed. | Technical | Owner | Day 3
4 | Fix SPA routes (/blog/, /demo/multilingual/, /aboutus) | JS-only pages often render empty to Googlebot. Add SSR/prerender or static HTML or they may NEVER index. | Technical | Dev/Owner | Day 4–5
5 | Request Indexing for Priority 2–3 URLs | Keep feeding Google the next batch within daily quota. | Technical | Owner | Day 6
6 | Submit URLs via IndexNow (Bing/Yandex) | Instant submission to Bing/Yandex; broad indexing health + referral signals. | Technical | Owner | Day 7
7 | Get 3–5 real backlinks (parent blogs, directories, Medium, relevant Reddit) | Dofollow links from crawled sites are far stronger discovery signals than social posts. | Off-site | Owner + team | Day 4–13
8 | Each person shares assigned links (Track B) | Social shares drive traffic + get URLs crawled from public pages Google scans. | Social | All 5 | Day 1–10
9 | Re-share stragglers on a 2nd platform | A second touch on a different network widens discovery for pages still not indexed. | Social | All 5 | Day 11–13
10 | Check thin/duplicate pages flagged 'Crawled – not indexed' | If content is thin, Google won't index it. Beef up to unique, useful, 600+ words. | Technical | Content/Owner | Day 12–14
11 | Daily index check: search site:mysleepytale.com/<path> | Tracks exactly which of the 50 are in. Update Status in the sheet. | Monitor | Owner | Daily
12 | Final review + fix-list for any remaining | Close out the sprint; plan targeted fixes for stubborn URLs. | Monitor | Owner | Day 15

## Link Distribution
# | Pri | URL | Topic | Owner | Suggested platform | Share by | Example post (copy, paste, add the link) | Status | Indexed?
1 | 1 | mysleepytale.com/blog/fifa-world-cup-kids-audiobook | World Cup Kids Audiobook | Sahil | X + IG story | Jun 15 | ⚽ World Cup buzz everywhere — turn it into calm bedtimes with World Cup audiobooks for kids. Goals by day, dreams by night. 🌙 #BedtimeStories #Parenting #KidsBooks #mysleepytale | Not shared | No
2 | 1 | mysleepytale.com/blog/fifa-world-cup-dallas-kids-audiobook | World Cup Dallas Kids Audiobook | Deepti | FB (Dallas groups) + IG | Jun 15 | Dallas families 🤠⚽ the World Cup is coming! Get your little fans excited with kid-friendly World Cup audiobooks. #BedtimeStories #Parenting #KidsBooks #mysleepytale | Not shared | No
3 | 1 | mysleepytale.com/blog/why-bedtime-stories-matter | Why Bedtime Stories Matter | Raksha | FB parent groups + IG | Jun 15 | Bedtime stories aren't just cute — they build vocabulary, empathy and calmer sleep. Here's the why (and how to start tonight). 🌙 #BedtimeStories #Parenting #KidsBooks #mysleepytale | Not shared | No
4 | 1 | mysleepytale.com/blog/screen-free-bedtime-routines | Screen-Free Bedtime Routines | Sarvanthi | FB parent groups + Pinterest | Jun 15 | Trying to cut screens before bed? 📵 Simple screen-free bedtime routines that actually work — plus audio stories to replace the scroll. #BedtimeStories #Parenting #KidsBooks #mysleepytale | Not shared | No
5 | 1 | mysleepytale.com/blog/indian-bedtime-stories | Indian Bedtime Stories | Prateek | FB community + WhatsApp | Jun 15 | From Panchatantra to modern tales 🪔 — Indian bedtime stories your kids will love, in languages they understand. #BedtimeStories #Parenting #KidsBooks #mysleepytale | Not shared | No
6 | 1 | mysleepytale.com/blog/islamic-stories-for-kids | Islamic Stories for Kids (blog) | Sahil | FB community + IG | Jun 16 | Beautiful Islamic stories for kids — values, kindness and gentle tales at bedtime. 🌙 #BedtimeStories #Parenting #KidsBooks #mysleepytale | Not shared | No
7 | 1 | mysleepytale.com/blog/best-bedtime-story-app-2026 | Best Bedtime Story App 2026 | Deepti | LinkedIn + X | Jun 16 | Looking for the best bedtime story app in 2026? An honest rundown of what to look for. 📱 #BedtimeStories #Parenting #KidsBooks #mysleepytale | Not shared | No
8 | 1 | mysleepytale.com/blog/best-bedtime-story-app-toronto | Best Bedtime Story App Toronto | Raksha | FB (Toronto groups) + IG | Jun 16 | Toronto parents 🇨🇦 — a bedtime story app made with local families in mind. Calm nights, happy mornings. #BedtimeStories #Parenting #KidsBooks #mysleepytale | Not shared | No
9 | 1 | mysleepytale.com/blog/multilingual-bedtime-stories | Multilingual Bedtime Stories | Sarvanthi | FB + WhatsApp groups | Jun 16 | Raising bilingual kids? 🌍 Bedtime stories in multiple languages help them keep their mother tongue — and fall asleep. #BedtimeStories #Parenting #KidsBooks #mysleepytale | Not shared | No
10 | 1 | mysleepytale.com/blog/become-a-creator | Become a Creator | Prateek | LinkedIn + X | Jun 16 | Love telling stories? ✍️ Become a creator on mysleepytale and share your tales with families everywhere. #BedtimeStories #Parenting #KidsBooks #mysleepytale | Not shared | No
11 | 2 | mysleepytale.com/blog/why-kids-love-who-would-win | Why Kids Love 'Who Would Win' | Sahil | FB parent groups + IG | Jun 17 | 'Who would win — a shark or a gorilla?' 🦈🦍 Ever wonder why kids are obsessed? Here's the psychology. #BedtimeStories #Parenting #KidsBooks #mysleepytale | Not shared | No
12 | 2 | mysleepytale.com/blog/why-kids-love-cars-buses | Why Kids Love Cars & Buses | Deepti | FB parent groups + IG | Jun 17 | 🚌 Why are toddlers SO into cars and buses? The reason is adorable (and developmental). #BedtimeStories #Parenting #KidsBooks #mysleepytale | Not shared | No
13 | 2 | mysleepytale.com/blog/why-kids-love-planets | Why Kids Love Planets | Raksha | FB + IG (STEM pages) | Jun 17 | 🪐 Space-obsessed little one? Why kids love planets — and how to feed that curiosity at bedtime. #BedtimeStories #Parenting #KidsBooks #mysleepytale | Not shared | No
14 | 2 | mysleepytale.com/blog/why-kids-love-sports-stories | Why Kids Love Sports Stories | Sarvanthi | X + FB | Jun 17 | ⚽🏀 Why sports stories light kids up — teamwork, heroes and big dreams. #BedtimeStories #Parenting #KidsBooks #mysleepytale | Not shared | No
15 | 2 | mysleepytale.com/blog/why-kids-need-superhero-stories | Why Kids Need Superhero Stories | Prateek | FB parent groups + IG | Jun 17 | 🦸 Superheroes aren't just fun — they teach courage, morality and resilience. Here's why they matter. #BedtimeStories #Parenting #KidsBooks #mysleepytale | Not shared | No
16 | 2 | mysleepytale.com/blog/why-family-stories-matter | Why Family Stories Matter | Sahil | FB + LinkedIn | Jun 18 | The stories about YOUR family are the ones kids remember most. ❤️ Why family stories matter. #BedtimeStories #Parenting #KidsBooks #mysleepytale | Not shared | No
17 | 2 | mysleepytale.com/blog/why-kids-love-countries | Why Kids Love Countries | Deepti | FB + IG | Jun 18 | 🌍 Kid fascinated by flags and faraway places? Why — and stories to travel the world at bedtime. #BedtimeStories #Parenting #KidsBooks #mysleepytale | Not shared | No
18 | 3 | mysleepytale.com/blog/hispanic-bedtime-stories-for-kids | Hispanic Bedtime Stories for Kids | Raksha | FB (Hispanic groups) + IG | Jun 18 | Cuentos para dormir 🌙 — Hispanic bedtime stories that celebrate culture and language. #BedtimeStories #Parenting #KidsBooks #mysleepytale | Not shared | No
19 | 3 | mysleepytale.com/blog/belief-stories-for-kids | Belief Stories for Kids | Sarvanthi | FB community + WhatsApp | Jun 18 | Gentle belief & values stories for kids — raising kind, thoughtful little humans. 🌙 #BedtimeStories #Parenting #KidsBooks #mysleepytale | Not shared | No
20 | 3 | mysleepytale.com/blog/kindergarten-learning-through-bedtime-stories | Kindergarten Learning via Stories | Prateek | FB (teacher groups) + LinkedIn | Jun 18 | Bedtime stories quietly teach kindergarten skills — letters, numbers, empathy — without it feeling like 'learning'. 📚 #BedtimeStories #Parenting #KidsBooks #mysleepytale | Not shared | No
21 | 3 | mysleepytale.com/blog/bluey-bingo-niagara-victoria-day | Bluey & Bingo Niagara | Sahil | FB (Niagara groups) + IG | Jun 19 | Bluey & Bingo fans near Niagara this Victoria Day! 🎉 A fun family pick. #BedtimeStories #Parenting #KidsBooks #mysleepytale | Not shared | No
22 | 3 | mysleepytale.com/blog/jean-lumb-kindergarten-bedtime-stories-toronto | Jean Lumb Kindergarten Toronto | Deepti | FB (Toronto school groups) | Jun 19 | Shoutout to Jean Lumb families in Toronto 🍁 — bedtime stories tailored for our kindergarteners. #BedtimeStories #Parenting #KidsBooks #mysleepytale | Not shared | No
23 | 3 | mysleepytale.com/blog/rainbow-kindergarten-series-2026 | Rainbow Kindergarten Series 2026 | Raksha | FB + IG | Jun 19 | 🌈 Introducing our Rainbow Kindergarten series for 2026 — learning + calm bedtimes in one. #BedtimeStories #Parenting #KidsBooks #mysleepytale | Not shared | No
24 | 4 | mysleepytale.com/blog/series-launch-animal-battles | Series: Animal Battles | Sarvanthi | IG + FB | Jun 19 | 🦁🐊 New series: Animal Battles! 'Who would win?' adventures kids can't get enough of. #BedtimeStories #Parenting #KidsBooks #mysleepytale | Not shared | No
25 | 4 | mysleepytale.com/blog/series-launch-little-astronaut | Series: Little Astronaut | Prateek | IG + FB (STEM) | Jun 19 | 🚀 New series: Little Astronaut! Blast off to dreamland with space adventures. #BedtimeStories #Parenting #KidsBooks #mysleepytale | Not shared | No
26 | 4 | mysleepytale.com/blog/series-launch-camping-outdoors | Series: Camping & Outdoors | Sahil | IG + FB | Jun 20 | 🏕️ New series: Camping & Outdoors — campfires, forests and cozy sleepy adventures. #BedtimeStories #Parenting #KidsBooks #mysleepytale | Not shared | No
27 | 4 | mysleepytale.com/blog/series-launch-music-lessons | Series: Music Lessons | Deepti | IG + FB | Jun 20 | 🎵 New series: Music Lessons — stories that introduce kids to the joy of music. #BedtimeStories #Parenting #KidsBooks #mysleepytale | Not shared | No
28 | 4 | mysleepytale.com/blog/series-launch-water-and-swim | Series: Water & Swim | Raksha | IG + FB | Jun 20 | 🏊 New series: Water & Swim — splashy adventures and water confidence for little ones. #BedtimeStories #Parenting #KidsBooks #mysleepytale | Not shared | No
29 | 4 | mysleepytale.com/blog/series-launch-maths-adventures | Series: Maths Adventures | Sarvanthi | FB (teacher groups) + IG | Jun 20 | ➗ New series: Maths Adventures — numbers made magical at bedtime. #BedtimeStories #Parenting #KidsBooks #mysleepytale | Not shared | No
30 | 4 | mysleepytale.com/blog/series-launch-geometry-shapes | Series: Geometry & Shapes | Prateek | FB (teacher groups) + IG | Jun 20 | 🔺🔵 New series: Geometry & Shapes — shape-spotting adventures for curious kids. #BedtimeStories #Parenting #KidsBooks #mysleepytale | Not shared | No
31 | 4 | mysleepytale.com/blog/series-launch-discover-india | Series: Discover India | Sahil | FB + WhatsApp | Jun 21 | 🇮🇳 New series: Discover India — culture, colours and tales from across India. #BedtimeStories #Parenting #KidsBooks #mysleepytale | Not shared | No
32 | 4 | mysleepytale.com/blog/series-launch-tallest-towers | Series: Tallest Towers | Deepti | IG + FB | Jun 21 | 🏗️ New series: Tallest Towers — wonders of the world for little builders. #BedtimeStories #Parenting #KidsBooks #mysleepytale | Not shared | No
33 | 4 | mysleepytale.com/blog/series-launch-planets-and-stars | Series: Planets & Stars | Raksha | IG + FB (STEM) | Jun 21 | ✨ New series: Planets & Stars — a gentle tour of the night sky at bedtime. #BedtimeStories #Parenting #KidsBooks #mysleepytale | Not shared | No
34 | 4 | mysleepytale.com/blog/technology-stack | Technology Stack | Sarvanthi | LinkedIn + X | Jun 21 | Curious how we build mysleepytale? 🛠️ A peek at our technology stack. #BuildInPublic #BedtimeStories #Parenting #KidsBooks #mysleepytale | Not shared | No
35 | 4 | mysleepytale.com/blog/security-improvements-guide | Security Improvements Guide | Prateek | LinkedIn + X | Jun 21 | Kids' safety first 🔒 — how we've strengthened security on mysleepytale. #BedtimeStories #Parenting #KidsBooks #mysleepytale | Not shared | No
36 | 4 | mysleepytale.com/blog/email-notifications-guide | Email Notifications Guide | Sahil | LinkedIn + X | Jun 22 | New: smarter email notifications so you never miss a new story or series. 📩 #BedtimeStories #Parenting #KidsBooks #mysleepytale | Not shared | No
37 | 4 | mysleepytale.com/blog/private-series-contributor-guide | Private Series Contributor Guide | Deepti | LinkedIn + FB | Jun 22 | Want to contribute private series for your family or school? Here's the guide. ✍️ #BedtimeStories #Parenting #KidsBooks #mysleepytale | Not shared | No
38 | 4 | mysleepytale.com/blog/creator-credits-guide | Creator Credits Guide | Raksha | LinkedIn + X | Jun 22 | How creator credits work on mysleepytale — get recognised for your stories. ✍️ #BedtimeStories #Parenting #KidsBooks #mysleepytale | Not shared | No
39 | 5 | mysleepytale.com/bedtime-stories-for-kids | Landing: Bedtime Stories for Kids | Sarvanthi | FB + X | Jun 22 | Bedtime stories for kids — calming tales that make nights easier for the whole family. 🌙 #BedtimeStories #Parenting #KidsBooks #mysleepytale | Not shared | No
40 | 5 | mysleepytale.com/bedtime-story-app | Landing: Bedtime Story App | Prateek | FB + X | Jun 22 | The bedtime story app built for modern families — screen-free, multilingual and soothing. 📱 #BedtimeStories #Parenting #KidsBooks #mysleepytale | Not shared | No
41 | 5 | mysleepytale.com/hindu-bedtime-stories | Landing: Hindu Bedtime Stories | Sahil | FB community + WhatsApp | Jun 23 | 🪔 Hindu bedtime stories — myths, values and gentle tales for little ones. #BedtimeStories #Parenting #KidsBooks #mysleepytale | Not shared | No
42 | 5 | mysleepytale.com/islamic-stories-for-kids | Landing: Islamic Stories for Kids | Deepti | FB community + IG | Jun 23 | 🌙 Islamic stories for kids — faith and kindness, told gently at bedtime. #BedtimeStories #Parenting #KidsBooks #mysleepytale | Not shared | No
43 | 5 | mysleepytale.com/catholic-bedtime-stories | Landing: Catholic Bedtime Stories | Raksha | FB community + IG | Jun 23 | ✝️ Catholic bedtime stories — faith-filled tales to end the day in peace. #BedtimeStories #Parenting #KidsBooks #mysleepytale | Not shared | No
44 | 5 | mysleepytale.com/hispanic-bedtime-stories | Landing: Hispanic Bedtime Stories | Sarvanthi | FB community + IG | Jun 23 | 🌙 Cuentos para niños — Hispanic bedtime stories celebrating language and culture. #BedtimeStories #Parenting #KidsBooks #mysleepytale | Not shared | No
45 | 5 | mysleepytale.com/sikh-bedtime-stories | Landing: Sikh Bedtime Stories | Prateek | FB community + WhatsApp | Jun 23 | 🪯 Sikh bedtime stories — values, history and gentle tales for kids. #BedtimeStories #Parenting #KidsBooks #mysleepytale | Not shared | No
46 | 5 | mysleepytale.com/fifa-world-cup-kids.html | FIFA World Cup Kids (page) | Sahil | X + IG | Jun 24 | ⚽ World Cup fever for the little ones! Kid-friendly World Cup stories & fun. #BedtimeStories #Parenting #KidsBooks #mysleepytale | Not shared | No
47 | 5 | mysleepytale.com/fifa-world-cup-dallas-kids.html | FIFA World Cup Dallas Kids (page) | Deepti | FB (Dallas) + X | Jun 24 | 🤠⚽ Dallas, the World Cup is coming! Get kids in the spirit with these fun stories. #BedtimeStories #Parenting #KidsBooks #mysleepytale | Not shared | No
48 | 6 | mysleepytale.com/blog/ | Blog index (SPA ⚠) | Raksha | X + LinkedIn + Reddit/Medium | Jun 24 | 📚 Our blog is full of parenting tips, story ideas and bedtime help. Dive in! #BedtimeStories #Parenting #KidsBooks #mysleepytale | Not shared | No
49 | 6 | mysleepytale.com/demo/multilingual/ | Multilingual Demo (SPA ⚠) | Sarvanthi | X + LinkedIn + Reddit | Jun 24 | 🌍 See it in action — try our multilingual bedtime stories demo! #BedtimeStories #Parenting #KidsBooks #mysleepytale | Not shared | No
50 | 6 | mysleepytale.com/aboutus | About Us (SPA ⚠) | Prateek | LinkedIn + X | Jun 24 | Meet the team behind mysleepytale — our mission for calmer, kinder bedtimes. 🌙 #BedtimeStories #Parenting #KidsBooks #mysleepytale | Not shared | No

## Daily Schedule (15 Days)
Day | Date | Focus | Social task (Track B) | Technical task (Track A) | Done?
1 | Mon Jun 15 | Kickoff + Priority 1 | Everyone shares their Day-1 link (Priority 1 set) on the suggested platform. | Verify GSC ownership; submit/re-submit sitemap.xml; confirm it's read.
2 | Tue Jun 16 | Ask Google directly | Share Day-2 link. | URL Inspection → Request Indexing for all Priority 1 URLs.
3 | Wed Jun 17 | Internal links | Share Day-3 link. | Add links from homepage + any indexed pages to Priority 1–2 URLs.
4 | Thu Jun 18 | Fix the SPA pages | Share Day-4 link. | Start SSR/prerender or static HTML for /blog/, /demo/multilingual/, /aboutus.
5 | Fri Jun 19 | Finish SPA + backlinks | Share Day-5 link. | Finish SPA fix; add the 3 SPA URLs to sitemap; line up 2 backlink targets.
6 | Sat Jun 20 | Priority 2 indexing | Share Day-6 link. | Request Indexing for Priority 2 URLs; post 1 Medium article linking 3 blogs.
7 | Sun Jun 21 | Wider net | Share Day-7 link. | Submit all 50 via IndexNow (Bing/Yandex); 1 relevant Reddit/forum post.
8 | Mon Jun 22 | 2nd platform push | Re-share your 2 best Priority 1 links on a different platform. | Request Indexing for Priority 3 URLs; check GSC coverage trend.
9 | Tue Jun 23 | Backlink outreach | Share Day-9 link. | Email 3–5 parent bloggers/partners for a link; submit to 2 directories.
10 | Wed Jun 24 | Last new links | Share Day-10 link. | Request Indexing for remaining landing pages; mid-sprint index count (site: checks).
11 | Thu Jun 25 | Catch stragglers | Re-share any link still not indexed on FB/WhatsApp groups. | List not-indexed URLs; check each for noindex/canonical/thin content issues.
12 | Fri Jun 26 | Internal links #2 | Team: drop links in 2 parent WhatsApp/FB groups each. | Add internal links FROM newly-indexed pages TO the not-yet-indexed ones.
13 | Sat Jun 27 | Second ask | Re-share stragglers on X/LinkedIn. | Second Request Indexing for stubborn URLs; secure 1–2 more backlinks.
14 | Sun Jun 28 | Fix thin pages | Light social re-share as needed. | Improve any 'Crawled – not indexed' pages (unique, 600+ words, clear value).
15 | Mon Jun 29 | Final validation | Celebrate wins; thank the groups that helped. 🙌 | Final site: + GSC count; log indexed total; write fix-list for any remaining.

## Indexing Checklist
✅ Real indexing levers (Track A) — work top to bottom
Task | Owner | Status
— GOOGLE SEARCH CONSOLE —
Verify the domain property in Search Console | Owner | ☐ To do
Submit / re-submit sitemap.xml and confirm 'Success' | Owner | ☐ To do
URL Inspection → Request Indexing for each Priority 1–2 URL (≈10–15/day quota) | Owner | ☐ To do
Watch the Pages report: track 'Discovered/Crawled – currently not indexed' | Owner | ☐ To do
— ON-SITE —
Confirm NO 'noindex' tag and robots.txt does not block these URLs | Dev/Owner | ☐ To do
Check canonical tags are self-referencing (not pointing elsewhere) | Dev/Owner | ☐ To do
Add internal links from homepage + indexed posts to all 50 URLs | Owner | ☐ To do
Strengthen thin pages → unique, useful, 600+ words | Content | ☐ To do
Confirm fast load + mobile-friendly (Core Web Vitals) | Dev | ☐ To do
— SPA FIX (critical for /blog/, /demo/multilingual/, /aboutus) —
Render content server-side / prerender so Googlebot sees real HTML | Dev | ☐ To do
Add the 3 SPA URLs to sitemap once they return static HTML | Dev | ☐ To do
Re-test with URL Inspection 'View crawled page' → content visible? | Owner | ☐ To do
— OFF-SITE / DISCOVERY —
Run the social distribution (Link Distribution tab) | All 5 | ☐ To do
Publish 1–2 Medium posts linking the top blogs (Google crawls Medium fast) | Owner | ☐ To do
Secure 3–5 real backlinks (parent blogs, directories, partners, relevant Reddit) | Owner + team | ☐ To do
Submit all URLs via IndexNow for Bing/Yandex | Owner | ☐ To do
— MONITOR —
Daily 'site:mysleepytale.com/<path>' checks → update Status in sheet | Owner | ☐ To do
Day 15: log indexed count + fix-list for any stragglers | Owner | ☐ To do

## Team Summary
📊 Team progress
Person | Links assigned | Shared | Indexed ✅ | % indexed
Sahil | 10 | 0 | 0 | 0%
Deepti | 10 | 0 | 0 | 0%
Raksha | 10 | 0 | 0 | 0%
Sarvanthi | 10 | 0 | 0 | 0%
Prateek | 10 | 0 | 0 | 0%
TOTAL | 50 | 0 | 0 | 0%
Update as you go: set Status + Indexed? in the 'Link Distribution' tab and these numbers refresh automatically. 🎯 Target by Day 15: 50/50 indexed.