## Start Here
🌙 mysleepytale — 30-Day Daily Content Plan
Daily Instagram + Platform X (Twitter) content, written and ready to schedule.
How this workbook is organised
📅 30-Day Calendar | Birds-eye view of all 30 days — theme per platform + status tracking.
📸 Instagram | Every day's reel concept, 10-sec voiceover script, caption, CTA & hashtags.
✖️ Platform X | Every day's build-in-public post (some are threads). Just copy & paste.
🛠️ Tools | Exactly which apps to use to make, narrate, design & schedule everything.
#️⃣ Hashtag & CTA Bank | Reusable hashtag sets and CTA lines to mix in.
The daily rhythm (what 'one day' looks like)
Instagram — 1 Reel / day | A 10-second teaser of that night's sleep story (calming visual + soft voiceover), caption, and the CTA: 'full story → link in bio, or DM us your thoughts.' 1–2 days a week swap to an engagement post (poll / tip / testimonial / behind-the-scenes) so the feed stays alive.
Platform X — 1 post / day | A short 'building in public' note about developing mysleepytale — decisions, lessons, wins, honest numbers, sneak peeks. Warmer & more personal than IG. A few days are threads.
Best times to post | IG Reels: aim for 8–10pm local (your audience is literally getting ready for bed). X: 7–9am or 9–11pm. Schedule a week at a time so you're never scrambling at night.
Content pillars (so it never feels repetitive)
Instagram | Platform X
• Story teasers (different mood every night: cosy, coastal, snowy, nostalgic) • Engagement (this-or-that polls, 'pick tonight's mood') • Sleep tips (breathing, routines) • Social proof (DMs / testimonials) • Behind-the-scenes (how a story is made) • Milestones | • The 'why' / origin story • Product & design decisions (+ the reasoning) • Behind-the-scenes of making a story • Lessons & honest mistakes • Real numbers / transparency • Feature sneak peeks • Questions to the audience • Founder reflections (the hard days too)
▸ Tip: 'Variety' days on the calendar are shaded gold. Everything else is a story-teaser reel. Swap any story title for one of your real ones — the structure stays the same.

## 📅 30-Day Calendar
Day | Date | Weekday | Instagram — theme | Platform X — theme | IG status | X status
1 | Jun 08 | Mon | The Last Train Home | Why I built this (thread) | To do | To do
2 | Jun 09 | Tue | The Lighthouse Keeper | What it is, in one line | To do | To do
3 | Jun 10 | Wed | A Cabin in the Snow | Design decision: no plot | To do | To do
4 | Jun 11 | Thu | The Tea Garden | Behind-the-scenes: writing for sleep | To do | To do
5 | Jun 12 | Fri | Drifting (a boat under stars) | Choosing the voice | To do | To do
6 | Jun 13 | Sat | The Old Bookshop | First story done (win) | To do | To do
7 | Jun 14 | Sun | POLL: night train vs snowy cabin | Question: what puts YOU to sleep? | To do | To do
8 | Jun 15 | Mon | Meadow at Dusk | Mistake: the too-exciting story | To do | To do
9 | Jun 16 | Tue | Grandmother's Kitchen | Lesson: the power of silence | To do | To do
10 | Jun 17 | Wed | The Desert Under Stars | Honest numbers, week 2 | To do | To do
11 | Jun 18 | Thu | Rain on a Tin Roof | Feature: the fade-out | To do | To do
12 | Jun 19 | Fri | The Slow River | Reflection: building in public is scary | To do | To do
13 | Jun 20 | Sat | A Greenhouse in Winter | Story craft: dissolve, don't end | To do | To do
14 | Jun 21 | Sun | TIP: the 4-7-8 breath | A DM that made my day | To do | To do
15 | Jun 22 | Mon | Tide Pools at Low Tide | Halfway recap (thread) | To do | To do
16 | Jun 23 | Tue | The Sleeping Village | Tech decision: instant playback | To do | To do
17 | Jun 24 | Wed | Lavender Fields | Library hits 8 stories | To do | To do
18 | Jun 25 | Thu | POLL: pick tonight's sleep mood | Poll: what to write next | To do | To do
19 | Jun 26 | Fri | The Ferry Crossing | The flat days are part of it | To do | To do
20 | Jun 27 | Sat | An Attic of Forgotten Things | Thinking out loud about pricing | To do | To do
21 | Jun 28 | Sun | TESTIMONIAL: your DMs | Recording day (behind-the-scenes) | To do | To do
22 | Jun 29 | Mon | A Field of Wheat | A detail I obsessed over | To do | To do
23 | Jun 30 | Tue | The Observatory | Why the pacing is so slow | To do | To do
24 | Jul 01 | Wed | The Houseboat | Shoutout to early users | To do | To do
25 | Jul 02 | Thu | The Quiet Cafe at Closing | Lesson: consistency > intensity | To do | To do
26 | Jul 03 | Fri | The Forest After Rain | Sneak peek: mood-matching | To do | To do
27 | Jul 04 | Sat | The Northern Lights | The hardest part of building this | To do | To do
28 | Jul 05 | Sun | BEHIND-THE-SCENES: how a story is made | Almost 30 days in | To do | To do
29 | Jul 06 | Mon | A Hammock Between Two Pines | Something's launching this week | To do | To do
30 | Jul 07 | Tue | MILESTONE: 30 nights, thank you | 30-day recap (thread) | To do | To do

## 📸 Instagram
Day | Date | Story / Post | Reel concept (the 10-sec visual) | Voiceover / on-screen text | Caption | CTA | Hashtags | Status
1 | Jun 08 | The Last Train Home | POV out a rain-streaked train window at night; warm carriage light; distant lights blurring past; title fades in. | “The last train of the night is almost empty. Rain taps the glass. The seat is warm. You don't have to be anywhere now… just here.” | Tonight's story: The Last Train Home. 🚂 A quiet carriage, rain on the windows, and nowhere you need to be. Let the rhythm of the rails carry you under. | 🌙 Full story → link in bio. Already drifting? DM us ONE word for how it made you feel. 💤 | #sleepstories #bedtimestories #fallasleepfast #sleephelp #calm #insomniarelief #cozyvibes #mysleepytale | To do
2 | Jun 09 | The Lighthouse Keeper | Slow pan of a lighthouse beam sweeping over a dark calm sea; stars; gentle waves below. | “High on the cliff, the lighthouse turns its slow, patient light. The sea breathes below. Tonight you are kept safe. Tonight you can rest.” | Tonight's story: The Lighthouse Keeper. 🌊 One steady light, one quiet sea, one slow breath after another. | 🌙 Full story → link in bio. Already drifting? DM us ONE word for how it made you feel. 💤 | #sleepstory #cantsleep #relaxation #sleepaid #nighttimeroutine #unwind #sleepbetter #mysleepytale | To do
3 | Jun 10 | A Cabin in the Snow | Crackling fireplace, embers glowing; snow falling past a frosted window; warm amber light. | “Snow falls without a sound. Inside, the fire settles into embers. The blanket is heavy and warm. Outside, the whole world is sleeping too.” | Tonight's story: A Cabin in the Snow. ❄️🔥 Snowfall, firelight, and the softest place to let your thoughts go quiet. | 🌙 Full story → link in bio. Already drifting? DM us ONE word for how it made you feel. 💤 | #bedtime #sleeptok #asmrvibes #winddown #restwell #sleepmeditation #cozyaesthetic #mysleepytale | To do
4 | Jun 11 | The Tea Garden | Japanese garden at dusk; paper lanterns glowing; soft rain on stone; koi-pond ripples. | “Rain falls gently on the garden stones. A lantern glows. Steam rises from a cup left to cool. There is nowhere to rush, nothing to solve.” | Tonight's story: The Tea Garden. 🏮 Lantern light, soft rain, and the slow art of doing nothing at all. | 🌙 Full story → link in bio. Already drifting? DM us ONE word for how it made you feel. 💤 | #sleepstories #bedtimestories #fallasleepfast #sleephelp #calm #insomniarelief #cozyvibes #mysleepytale | To do
5 | Jun 12 | Drifting (a boat under stars) | Tiny rowboat on a glassy lake at night; vast field of stars; almost imperceptible bobbing. | “The boat rocks so slightly you can barely feel it. Above you, more stars than you could ever count. You let the water hold you.” | Tonight's story: Drifting. ✨ A still lake, a sky full of stars, and the gentle feeling of being carried. | 🌙 Full story → link in bio. Already drifting? DM us ONE word for how it made you feel. 💤 | #sleepstory #cantsleep #relaxation #sleepaid #nighttimeroutine #unwind #sleepbetter #mysleepytale | To do
6 | Jun 13 | The Old Bookshop | Candlelit bookshop after closing; dust motes; rain on the window; rows of old books in warm low light. | “The shop has closed for the night. Rain on the window, a single candle, and a thousand quiet stories waiting on the shelves.” | Tonight's story: The Old Bookshop. 📚 Candlelight, rain, and the hush of a room that's held a hundred years of words. | 🌙 Full story → link in bio. Already drifting? DM us ONE word for how it made you feel. 💤 | #bedtime #sleeptok #asmrvibes #winddown #restwell #sleepmeditation #cozyaesthetic #mysleepytale | To do
7 | Jun 14 | POLL — night train vs snowy cabin [VARIETY] | Split-screen reel: left = cosy train carriage, right = snowy cabin. Big text 'Which one sends YOU to sleep?' + tap-to-vote sticker. | On-screen: “Which one knocks you out faster — the night train 🚂 or the cabin in the snow ❄️? Vote 👇” | We're writing more stories and we want yours to win. 🚂 vs ❄️ — which setting puts you out instantly? Tap the sticker, then tell us in the comments where YOU'D fall asleep. | Vote on the sticker + comment your pick. Winner gets written this week. 🌙 | #sleepstories #bedtimestories #fallasleepfast #sleephelp #calm #insomniarelief #cozyvibes #mysleepytale | To do
8 | Jun 15 | Meadow at Dusk | Golden meadow; fireflies rising as the light fades; warm grass swaying slowly. | “The day lets go slowly. Fireflies lift from the grass like sleepy little stars. The warmth of the afternoon still lingers on your skin.” | Tonight's story: Meadow at Dusk. 🌾 Fireflies, fading gold light, and the gentle hush of a day winding down. | 🌙 Full story → link in bio. Already drifting? DM us ONE word for how it made you feel. 💤 | #sleepstory #cantsleep #relaxation #sleepaid #nighttimeroutine #unwind #sleepbetter #mysleepytale | To do
9 | Jun 16 | Grandmother's Kitchen | Warm vintage kitchen at night; soft lamp; a clock ticking; bread under a cloth; faint steam. | “The kitchen still smells of warm bread. A clock ticks softly on the wall. Here, you were always safe. Here, you can finally let go.” | Tonight's story: Grandmother's Kitchen. 🍞 Warm bread, a ticking clock, and the kind of safe that makes your shoulders drop. | 🌙 Full story → link in bio. Already drifting? DM us ONE word for how it made you feel. 💤 | #bedtime #sleeptok #asmrvibes #winddown #restwell #sleepmeditation #cozyaesthetic #mysleepytale | To do
10 | Jun 17 | The Desert Under Stars | Vast desert at night; dunes cooling; enormous starry sky; very slow drift across the sand. | “The sand is still warm from the sun, but the night air is cool now. The sky is enormous and quiet. Out here, your worries feel very small.” | Tonight's story: The Desert Under Stars. 🌌 Warm sand, cool air, and a sky so wide your mind finally goes quiet. | 🌙 Full story → link in bio. Already drifting? DM us ONE word for how it made you feel. 💤 | #sleepstories #bedtimestories #fallasleepfast #sleephelp #calm #insomniarelief #cozyvibes #mysleepytale | To do
11 | Jun 18 | Rain on a Tin Roof | Close-up rain on a tin roof; water running down a window; dim warm interior. | “Just rain. Steady on the roof above you. No story to follow, nowhere to be. Only the sound, and your slow, easy breathing.” | Tonight's story: Rain on a Tin Roof. 🌧️ Pure rain, a warm bed, and nothing your mind has to do but listen. | 🌙 Full story → link in bio. Already drifting? DM us ONE word for how it made you feel. 💤 | #sleepstory #cantsleep #relaxation #sleepaid #nighttimeroutine #unwind #sleepbetter #mysleepytale | To do
12 | Jun 19 | The Slow River | Floating downstream; overhanging willows; dappled moonlight on slow-moving water. | “The river is in no hurry. It carries you past sleeping willows, under a soft moon — slowly, slowly — towards somewhere kind.” | Tonight's story: The Slow River. 🌙 Drifting downstream under the willows, with nowhere to be but here. | 🌙 Full story → link in bio. Already drifting? DM us ONE word for how it made you feel. 💤 | #bedtime #sleeptok #asmrvibes #winddown #restwell #sleepmeditation #cozyaesthetic #mysleepytale | To do
13 | Jun 20 | A Greenhouse in Winter | Warm glass greenhouse; frost on the outside; lush plants inside; soft lamplight; condensation. | “Outside, frost. Inside the glass, it's warm and green and growing. The air is soft and damp. Everything in here is quietly alive — and resting.” | Tonight's story: A Greenhouse in Winter. 🌿 Frost on the glass, warmth within, and the slow breathing of growing things. | 🌙 Full story → link in bio. Already drifting? DM us ONE word for how it made you feel. 💤 | #sleepstories #bedtimestories #fallasleepfast #sleephelp #calm #insomniarelief #cozyvibes #mysleepytale | To do
14 | Jun 21 | TIP — the 4-7-8 breath [VARIETY] | Calm b-roll (dim bedroom, a hand turning off a lamp) with clean text overlays teaching the breath; soft voiceover. ~20-30 sec. | “Can't switch your brain off? Breathe in for 4, hold for 7, out for 8. Three rounds. It slows your heart on purpose. We build it into every story — that's why people drift off before the ending.” | Why do our listeners fall asleep before the story ends? 😴 It's not magic — it's pacing. Here's the 4-7-8 breath we weave into every mysleepytale. Save this for tonight. 🔖 | Save this 🔖 + try it tonight. Then DM us if it worked. 🌙 | #sleepstory #cantsleep #relaxation #sleepaid #nighttimeroutine #unwind #sleepbetter #mysleepytale | To do
15 | Jun 22 | Tide Pools at Low Tide | Moonlit rocky shore; still tide pools reflecting stars; very gentle distant waves. | “The tide has gone out. Little pools hold pieces of the moon. The sea whispers far away. The whole shore is still — and so are you.” | Tonight's story: Tide Pools at Low Tide. 🌊 Moonlit pools, a distant sea, and a shore that's perfectly, peacefully still. | 🌙 Full story → link in bio. Already drifting? DM us ONE word for how it made you feel. 💤 | #bedtime #sleeptok #asmrvibes #winddown #restwell #sleepmeditation #cozyaesthetic #mysleepytale | To do
16 | Jun 23 | The Sleeping Village | Hilltop view over a tiny village at night; warm window lights going dark one by one. | “From up here, the village is sleeping. One by one, the warm little windows go dark. Soon there's only the stars — and you, letting go too.” | Tonight's story: The Sleeping Village. 🏘️ Watching the last lights go out, one gentle window at a time. | 🌙 Full story → link in bio. Already drifting? DM us ONE word for how it made you feel. 💤 | #sleepstories #bedtimestories #fallasleepfast #sleephelp #calm #insomniarelief #cozyvibes #mysleepytale | To do
17 | Jun 24 | Lavender Fields | Rows of lavender at golden hour fading to dusk; soft bees; warm purple haze. | “Rows of lavender stretch to the horizon, soft and purple in the last light. The air is warm and sweet. Breathe it in. Let it carry you down.” | Tonight's story: Lavender Fields. 💜 Endless rows, warm evening air, and a scent that tells your body it's safe to rest. | 🌙 Full story → link in bio. Already drifting? DM us ONE word for how it made you feel. 💤 | #sleepstory #cantsleep #relaxation #sleepaid #nighttimeroutine #unwind #sleepbetter #mysleepytale | To do
18 | Jun 25 | POLL — pick tonight's sleep mood [VARIETY] | Dreamy reel cycling through 4 settings (sea / forest / train / fire) with text 'What's your sleep mood tonight?' + emoji options. | On-screen: “Pick your sleep mood: 🌊 Sea · 🌲 Forest · 🚂 Train · 🔥 Fire. Comment your pick — we'll feature the winner this weekend.” | Help us pick this weekend's story. 🌊🌲🚂🔥 What's your sleep mood tonight? Drop your emoji below — the most-voted setting gets written and narrated for you. | Comment your emoji 👇 Most votes gets made this weekend. 🌙 | #bedtime #sleeptok #asmrvibes #winddown #restwell #sleepmeditation #cozyaesthetic #mysleepytale | To do
19 | Jun 26 | The Ferry Crossing | Night ferry on calm dark water; gentle deck lights; soft engine hum; distant harbour lights. | “The ferry hums softly across the calm, dark water. The deck rocks gently. The lights of the far shore glow, patient, in no hurry for you to arrive.” | Tonight's story: The Ferry Crossing. ⛴️ A gentle hum, a rocking deck, and a far shore that will wait until morning. | 🌙 Full story → link in bio. Already drifting? DM us ONE word for how it made you feel. 💤 | #sleepstories #bedtimestories #fallasleepfast #sleephelp #calm #insomniarelief #cozyvibes #mysleepytale | To do
20 | Jun 27 | An Attic of Forgotten Things | Warm dusty attic; one small window of moonlight; soft sheets over old furniture; safe, nostalgic. | “The attic is full of soft, forgotten things. Moonlight through one small window. Up here, time slows down — and nothing can reach you.” | Tonight's story: An Attic of Forgotten Things. 🕯️ Dust, moonlight, and the safe hush of a room that time forgot. | 🌙 Full story → link in bio. Already drifting? DM us ONE word for how it made you feel. 💤 | #sleepstory #cantsleep #relaxation #sleepaid #nighttimeroutine #unwind #sleepbetter #mysleepytale | To do
21 | Jun 28 | TESTIMONIAL — your DMs [VARIETY] | Reel of anonymised DM screenshots ('first time in years I'm not scared of bedtime') over calm b-roll; warm gentle music. | On-screen: “Some of the messages you've been sending us… 🥹 We read every single one.” | We started mysleepytale because WE couldn't sleep. Reading messages like these is everything. 💌 If a story helped you drift off, reply or DM us — with your ok, we might (anonymously) feature it. Goodnight. 🌙 | DM us your story 💌 (anonymous, only with your ok). 🌙 | #bedtime #sleeptok #asmrvibes #winddown #restwell #sleepmeditation #cozyaesthetic #mysleepytale | To do
22 | Jun 29 | A Field of Wheat | Golden wheat field swaying slowly at dusk; warm wind; soft seed heads; fading light. | “The wheat sways in a warm, slow wind. Gold turning to grey as the light fades. The whole field breathes with you. In. And out. And down.” | Tonight's story: A Field of Wheat. 🌾 A warm wind, swaying gold, and the slow rhythm of a field at dusk. | 🌙 Full story → link in bio. Already drifting? DM us ONE word for how it made you feel. 💤 | #sleepstories #bedtimestories #fallasleepfast #sleephelp #calm #insomniarelief #cozyvibes #mysleepytale | To do
23 | Jun 30 | The Observatory | Observatory dome slowly opening to the night sky; slow rotation; soft mechanical hum; vast stars. | “The great dome opens slowly to the sky. Stars wheel overhead, patient and ancient. You lie back. The whole universe is happy to wait for you.” | Tonight's story: The Observatory. 🔭 A slow-opening dome, a sky full of ancient stars, and all the time in the world. | 🌙 Full story → link in bio. Already drifting? DM us ONE word for how it made you feel. 💤 | #sleepstory #cantsleep #relaxation #sleepaid #nighttimeroutine #unwind #sleepbetter #mysleepytale | To do
24 | Jul 01 | The Houseboat | Small houseboat on a still canal at night; gentle rocking; warm cabin light; water lapping. | “The houseboat rocks so gently on the still canal. Water laps softly against the hull. The little cabin is warm. The night is yours, and it is calm.” | Tonight's story: The Houseboat. 🛶 Gentle rocking, lapping water, and a warm little cabin floating you off to sleep. | 🌙 Full story → link in bio. Already drifting? DM us ONE word for how it made you feel. 💤 | #bedtime #sleeptok #asmrvibes #winddown #restwell #sleepmeditation #cozyaesthetic #mysleepytale | To do
25 | Jul 02 | The Quiet Cafe at Closing | Cosy cafe after hours; chairs up on tables; warm low light; rain on the window; one last cup steaming. | “The cafe has closed. Chairs rest on the tables. Rain on the window, one warm lamp still on. The day is done now. You did enough. Rest.” | Tonight's story: The Quiet Cafe at Closing. ☕ Rain outside, one warm lamp, and permission to finally set the day down. | 🌙 Full story → link in bio. Already drifting? DM us ONE word for how it made you feel. 💤 | #sleepstories #bedtimestories #fallasleepfast #sleephelp #calm #insomniarelief #cozyvibes #mysleepytale | To do
26 | Jul 03 | The Forest After Rain | Misty forest just after rain; drips from leaves; soft green light; slow drifting fog. | “The rain has stopped. The forest drips softly, slowly. Mist drifts between the trees. The earth smells sweet and clean. Breathe it in. You're safe here.” | Tonight's story: The Forest After Rain. 🌲 Soft drips, drifting mist, and the sweet clean hush after the storm. | 🌙 Full story → link in bio. Already drifting? DM us ONE word for how it made you feel. 💤 | #sleepstory #cantsleep #relaxation #sleepaid #nighttimeroutine #unwind #sleepbetter #mysleepytale | To do
27 | Jul 04 | The Northern Lights | Lying back in soft snow looking up; green-and-violet aurora rippling slowly across the stars. | “You lie back in the soft snow. Above you, the lights begin to move — green and violet, slow as a dream. There's nothing to do but watch, and let go.” | Tonight's story: The Northern Lights. 🌌 Soft snow below, slow ribbons of colour above, and a sky that asks nothing of you. | 🌙 Full story → link in bio. Already drifting? DM us ONE word for how it made you feel. 💤 | #bedtime #sleeptok #asmrvibes #winddown #restwell #sleepmeditation #cozyaesthetic #mysleepytale | To do
28 | Jul 05 | BEHIND-THE-SCENES — how a story is made [VARIETY] | Calm montage: writing a script, a mic in a softly lit room, a sound-design waveform, headphones; text overlays explaining the craft. | On-screen: “How a mysleepytale is made — ✍️ written slow on purpose · 🎙️ narrated just above a whisper · 🎧 layered with sound so soft you stop noticing it. All so you fall asleep before the ending.” | Ever wonder why these actually work? 🎙️ Here's how one story comes together — written slow, narrated soft, mixed to fade you out. Which step surprised you? DM us. 🌙 | DM us which step surprised you 🌙 | #sleepstories #bedtimestories #fallasleepfast #sleephelp #calm #insomniarelief #cozyvibes #mysleepytale | To do
29 | Jul 06 | A Hammock Between Two Pines | Hammock swaying gently between two tall pines at dusk; warm dappled gold light; slow sway. | “The hammock sways between two tall pines. The breeze is warm. The light comes down soft and gold through the branches. Sway. And settle. And sleep.” | Tonight's story: A Hammock Between Two Pines. 🌲 A warm breeze, a gentle sway, and the easiest place in the world to let go. | 🌙 Full story → link in bio. Already drifting? DM us ONE word for how it made you feel. 💤 | #sleepstory #cantsleep #relaxation #sleepaid #nighttimeroutine #unwind #sleepbetter #mysleepytale | To do
30 | Jul 07 | MILESTONE — 30 nights, thank you [VARIETY] | Warm montage of the month's settings flashing softly by; ends on '30 nights. Thank you.' + a candle being blown out. | On-screen: “30 stories. 30 nights. Thousands of you drifting off with us. This is just the beginning. 🌙 Thank you for falling asleep with mysleepytale.” | 30 days. 30 stories. And so many of you sleeping better. 🥹 Thank you for being here from the start. Which story was YOUR favourite this month? The most-loved one gets a sequel. 💤 Goodnight — and here's to the next 30. 🌙 | Comment your favourite story 👇 It gets a sequel. 🌙 | #bedtime #sleeptok #asmrvibes #winddown #restwell #sleepmeditation #cozyaesthetic #mysleepytale | To do

## ✖️ Platform X
Day | Date | Pillar | Format | Post (copy & paste) | Status
1 | Jun 08 | Why I built this | Thread (2 posts) | I couldn't sleep for most of 2 years. Not the romantic kind of insomnia. The 3am, staring-at-the-ceiling, dreading-tomorrow kind. So I started building the thing I wished existed. It's called mysleepytale, and I'm going to build it in public. 🧵 ——— 2/ Every sleep app I tried did one of two things: rain sounds on a loop, or a story so interesting I stayed up to hear the end. I wanted the opposite. A story warm enough to follow, boring enough to lose. Designed to make you stop listening. | To do
2 | Jun 09 | What it is, in one line | Single post | mysleepytale in one line: short, narrated bedtime stories, written and paced specifically to make you fall asleep before they end. That last part is the whole product. If you hear the ending, I failed. | To do
3 | Jun 10 | Design decision: no plot | Single post | Design decision I keep defending: no plot. People expect stories to build toward something. But tension keeps you awake. So mysleepytale stories go nowhere on purpose — a train ride, a quiet garden, a slow river. The reward isn't the ending. It's the drifting. | To do
4 | Jun 11 | Behind-the-scenes: writing for sleep | Single post | Spent today writing 'The Lighthouse Keeper.' Writing for sleep is strange. I delete every sentence that's too interesting. No conflict, no surprises, no clever turns. It feels wrong as a writer. It works as a sleep aid. That tension is the job. | To do
5 | Jun 12 | Choosing the voice | Single post | Voice test today. Tried 6 versions of the same paragraph: neutral, warm, slow, slower, near-whisper, and one that was honestly a bit much. The winner wasn't the slowest. It was the one that sounded like someone who genuinely wanted you to rest. Warmth > technique. | To do
6 | Jun 13 | First story done (win) | Single post | First full story is done. 🌙 Written, narrated, scored, mixed. 11 minutes long — but the goal is you never make it past minute 4. Tested it on myself last night. Don't remember the last 7 minutes. I'll call that a win. | To do
7 | Jun 14 | Question: what puts you to sleep? | Single post | Genuine question for the sleepless among you: What actually puts YOU to sleep? Rain? A voice? Total silence? A specific memory you replay? I'm collecting these to write better stories. Reply with yours — I read every one. | To do
8 | Jun 15 | Mistake: the too-exciting story | Single post | Mistake of the week. Wrote a story set on a night train. Added a 'mysterious stranger boards at the next stop' to make it interesting. Three testers messaged me: 'I HAD to know who it was. Stayed up till 1.' Cut the stranger. Tension is the enemy here. | To do
9 | Jun 16 | Lesson: the power of silence | Single post | Underrated tool in sleep audio: silence. Early versions had wall-to-wall narration. Felt safe, sounded suffocating. Now I leave long gaps. Rain, a breath, nothing. The gaps are where people actually drift off. Turns out the pauses do the work. | To do
10 | Jun 17 | Honest numbers, week 2 | Single post | Honest numbers, week 2: → 4 stories live → ~340 listens → 61% don't finish (this is GOOD — it's the point) → 9 DMs that made me a bit emotional Small. But 340 people tried to sleep with something I made. That's wild to me. | To do
11 | Jun 18 | Feature: the fade-out | Single post | Tiny feature, weirdly hard: the fade-out. When a story ends, it can't just STOP — that jolts you awake. So the last 90 seconds slowly dissolve into rain, then nothing. Spent a full day on 90 seconds of fading. Worth it. | To do
12 | Jun 19 | Reflection: building in public is scary | Single post | Building in public is scary in a specific way: I'm not shipping a SaaS dashboard. I'm shipping the thing I made for my own worst nights. Every time someone says 'this helped,' it's not a metric. It's the most personal feedback I've ever gotten. | To do
13 | Jun 20 | Story craft: dissolve, don't end | Single post | Story craft lesson I didn't expect: A sleep story shouldn't end. It should dissolve. No conclusion, no 'and so.' Just a scene getting quieter and quieter until you're not sure where the story stopped and your dream began. Endings wake people. Dissolves don't. | To do
14 | Jun 21 | A DM that made my day | Single post | Got this DM last night: 'I've listened to the cabin one for 5 nights straight. First time in years I'm not scared of bedtime.' I built this for 3am-me. Knowing it reached someone else's 3am is the only metric I actually care about. 🌙 | To do
15 | Jun 22 | Halfway recap | Thread (3 posts) | Halfway through building mysleepytale in public. Quick recap + what's next. 🧵 What I've learned in 15 days: ——— 2/ 1. Boring is a feature, not a bug. 2. Silence does more than narration. 3. The fade-out matters as much as the story. 4. People don't want plot at bedtime. They want safety. ——— 3/ What's next: → 10 more stories (mood-based: sea, forest, winter) → a sleep timer that fades, not cuts → figuring out if this is free or a tiny-subscription thing Still building in the open. Thanks for being here. | To do
16 | Jun 23 | Tech decision: instant playback | Single post | Tech decision: stories stream, but the first 3 minutes pre-cache. Why? Because the worst thing for a sleepless brain is a buffering spinner at 2am. It has to start instantly, every time, even on bad wifi. Reliability IS the calm. | To do
17 | Jun 24 | Library hits 8 stories | Single post | The library hit 8 stories today. 🌙 Themes so far: a night train, a lighthouse, a snowy cabin, a tea garden, a slow river, an old bookshop, a meadow, a desert at night. Noticing a pattern: warmth + going nowhere. That's apparently my whole genre now. | To do
18 | Jun 25 | Poll: what to write next | Single post | Help me pick what to write next. What setting would put YOU under fastest? 🌊 quiet sea 🌲 misty forest 🚂 night train 🔥 cabin by a fire Most-voted gets written, narrated, and shipped this week. Reply or vote. | To do
19 | Jun 26 | The flat days are part of it | Single post | Not every day building this feels good. Today I recorded the same intro 30 times and hated all of them. Questioned whether anyone needs another sleep thing. Then reread one DM. Closed the laptop. Tomorrow I record take 31. Building in public includes the flat days. | To do
20 | Jun 27 | Thinking out loud about pricing | Single post | Thinking out loud about pricing. Sleep feels like something that shouldn't be paywalled. But hosting + narration + sound design cost real money. Leaning toward: a free library that's actually good, plus a small subscription for new stories weekly. Is that fair? | To do
21 | Jun 28 | Recording day (behind-the-scenes) | Single post | Recording day. ☕🎙️ What it actually looks like: a closet full of duvets for soundproofing, one mic, one lamp, and reading the same warm sentence until my voice stops 'performing' and just… softens. The good takes happen when I'm a little sleepy myself. | To do
22 | Jun 29 | A detail I obsessed over | Single post | A detail almost nobody will notice, that I obsessed over: Story titles have no exclamation points. No 'AMAZING SLEEP STORY.' Just: The Slow River. The Old Bookshop. A Cabin in the Snow. The calm has to start before you press play. | To do
23 | Jun 30 | Why the pacing is so slow | Single post | Why every mysleepytale is paced so slowly: It's not laziness — it's matched to your breathing. The sentences lengthen, the pauses grow, the voice drops. By minute 3 your breath is following the narration down. You don't notice. That's the design. | To do
24 | Jul 01 | Shoutout to early users | Single post | Shoutout to the ~20 people who've been here since story #1. You reply to my posts at midnight (relatable), you tell me which stories work, you DM me when one helps. mysleepytale is being built by a sleepless community, not just me. Thank you. 🌙 | To do
25 | Jul 02 | Lesson: consistency > intensity | Single post | Lesson from 25 days of building in public: Consistency beats intensity. One small honest post a day did more than any 'big launch' would've. Same as the product, actually. You don't fall asleep from one perfect night. You fall asleep from a gentle routine. | To do
26 | Jul 03 | Sneak peek: mood-matching | Single post | Sneak peek 👀 Working on mood-matched stories: tell the app how your mind feels tonight — racing, sad, wired, heavy — and it picks the story (and the pacing) built for that state. Different nights need different calm. Building for that now. | To do
27 | Jul 04 | The hardest part of building this | Single post | The hardest part of building mysleepytale isn't the tech or the writing. It's that I can only test it properly when I'm exhausted and desperate to sleep — the exact state I'm designing for. My best product research happens at 2am, half-asleep. Strange job. | To do
28 | Jul 05 | Almost 30 days in | Single post | Almost at 30 days of building this in public. Where we are: → 12 stories live → a fade-out sleep timer → mood-matching in progress → a small, kind community of insomniacs What started as a fix for my own 3am is becoming something real. 🌙 | To do
29 | Jul 06 | Something's launching this week | Single post | Something's launching this week. 👀 A small, free starter collection of mysleepytale stories — the ones that tested best on the worst nights. If you've ever lain awake dreading the morning, this was built for you. Drop a 🌙 and I'll make sure you're first to know. | To do
30 | Jul 07 | 30-day recap | Thread (4 posts) | 30 days of building mysleepytale in public. Here's everything I learned. 🧵🌙 ——— 2/ On the product: → Boring is the feature. → Silence narrates better than words. → Don't end a story. Dissolve it. → Reliability at 2am is the real 'calm.' → Slow pacing = matched breathing. ——— 3/ On building in public: → One honest post a day > any launch. → The flat days are part of it. → Your DMs kept me going more than any metric. → I built this for 3am-me, and found a few thousand others who needed it too. ——— 4/ Where we go next: more stories. Mood-matching. A real home for all of it. If you've read this far: thank you. Go to sleep. 🌙 (And if tonight's a hard one — mysleepytale is here.) | To do

## 🛠️ Tools
🛠️ The mysleepytale tool stack
A lean, mostly-free setup. You don't need all of these — the ⭐ rows are the minimum to run everything.
Job | Tool | Cost | Why / notes
⭐ Write the stories & this plan | ChatGPT / Claude | Free–$ | Draft and refine story scripts, captions, and X posts. Paste a setting, ask for a 'slow, plotless, calming' story.
⭐ Narrate (AI voice) | ElevenLabs | Free tier / ~$5+/mo | Best natural, warm AI narration for sleep. Pick a soft voice, slow the speed. (Or record your own voice — see below.)
Narrate (your own voice) | Phone + a quiet room | Free | A duvet-lined closet + phone mic genuinely works. Most authentic for a personal brand.
Voice + video in one | Fliki | Free tier / ~$/mo | Turns a script into a narrated, captioned vertical video fast — handy if you want voice + visuals together.
⭐ Make the Reels | CapCut | Free | The standard for Reels/TikTok in 2026. Auto-captions, trendy templates, vertical export, AI tools. Mobile + desktop.
Reels (browser, captions) | VEED.io | Free / $18/mo | Edit in the browser, strong auto-captions and AI voiceover. Good if you dislike timeline apps.
⭐ Graphics, covers, thumbnails | Canva | Free / Pro | Story covers, quote cards, carousel posts, consistent fonts & colours. Has its own simple video editor too.
Calming visuals / b-roll | Pexels, Pixabay | Free | Free stock video of rain, fireplaces, oceans, snow — exactly the moods your stories need. No licence worries.
Calm music & ambience | Reels audio library; Epidemic Sound | Free / ~$/mo | Use Reels' in-app trending audio for reach; Epidemic for licensed calm beds on your own site/app.
⭐ Schedule IG + X | Later (free) or Buffer (free) | Free | Later free: 1 set incl. IG + X, ~30 posts/mo, visual feed planner (great for IG). Buffer free: 3 channels, 10 queued each.
Native IG scheduling | Meta Business Suite | Free | Free, official, schedules IG feed/Reels. No frills, but reliable. Note: can't schedule Stories.
Heads-up on X scheduling | — | — | In 2026 several 'free' schedulers dropped X (higher API cost). Later still includes it free; Buffer includes it; double-check before relying on it.
Track performance | Instagram Insights + Metricool | Free | See which story moods + posting times actually drive saves, shares and DMs — then make more of what works.
▸ Minimum viable stack (all free): Claude/ChatGPT to write → ElevenLabs OR your own voice to narrate → CapCut to cut the 10-sec Reel → Canva for the cover → Later to schedule IG + X. That's the whole machine.

## #️⃣ Hashtag & CTA Bank
#️⃣ Reusable hashtags & CTAs
Rotate sets so IG doesn't flag you for spammy repetition. Mix ~8–12 tags per post: a few big, a few niche.
Hashtag sets (rotate daily)
Set A — core | #sleepstories #bedtimestories #fallasleepfast #sleephelp #calm #insomniarelief #cozyvibes #mysleepytale
Set B — searchy | #sleepstory #cantsleep #relaxation #sleepaid #nighttimeroutine #unwind #sleepbetter #mysleepytale
Set C — aesthetic | #bedtime #sleeptok #asmrvibes #winddown #restwell #sleepmeditation #cozyaesthetic #mysleepytale
Set D — niche/intent | #insomnia #anxietyrelief #calmingsounds #sleeproutine #goodnight #deepsleep #bedtimestory #mysleepytale
Always include | #mysleepytale (your branded tag — ask listeners to use it too)
CTA lines (swap to keep it fresh)
CTA 1 | 🌙 Full story → link in bio. Already drifting? DM us ONE word for how it made you feel. 💤
CTA 2 | Press play tonight → link in bio. Then DM us where it took you. 🌙
CTA 3 | Save this for 3am 🔖 Full version in bio. Sweet dreams.
CTA 4 | Couldn't make it to the end? That's the point. 😴 Full story → link in bio.
CTA 5 | Tell us: did you fall asleep before it finished? DM us 🌙 Full version in bio.
CTA 6 | Tag someone who needs a better night's sleep 💤 Full story in bio.
CTA 7 | Comment 🌙 and we'll DM you tonight's full story.
▸ One link, many destinations: put a Linktree / Beacons in your bio so 'link in bio' can point to your story, app, or signup — and you never have to change the bio daily.